## MAIN MENU
Name:
Personal Time: | 0
Whole Team Time: | 15.55
TOTAL: | 15.55

## PUT THE ITERATION DATA HERE
Assignee | Iteration | Status | ID | Depends On | Description | Importance | Estimated Time | Actual Hours | Comments | Estimated Hours | Difference | Value | Estimated Value / Hour | Actual Value / Hour
Whole Team | 2 | Done | 1 |  | Goal-setting | Must | a few minutes | 0.2 |  | 0.2 | 0 | 89 | 445 | 445
Sean Miyaoka | 2 | Done | 8 |  | Github setup | Must | a few minutes | 0.1 |  | 0.2 | -0.1 | 89 | 445 | 890
Stephanie Reed | 2 | Done | 9 |  | Ask questions about scrumboard and frameworks | Must | a few minutes | 0.15 | Answers on Discord | 0.2 | -0.1 | 89 | 445 | 593.33
Whole Team | 2 | Done | 10 |  | Firebase Meeting | Must | a few minutes | 0.15 |  | 0.2 | -0.1 | 89 | 445 | 593.33
Stephanie Reed | 2 | Done | 18 |  | Upload documents to new doc repository | Must | a few minutes | 0.15 |  | 0.2 | -0.1 | 89 | 445 | 593.33
Whole Team | 2 | Done | 38 |  | Book lab sessions | Must | a few minutes | 0.5 |  | 0.2 | 0.3 | 89 | 445 | 178
Whole Team | 2 | Done | 3 |  | Decide on the definition of "Done" | Must | half an hour | 0.2 | Posted on Discord | 0.5 | -0.3 | 89 | 178 | 445
Stephanie Reed | 2 | Done | 11 |  | Github Gitflow Branch and naming convention setup | Must | half an hour | 0.6 |  | 0.5 | 0.1 | 89 | 178 | 148.33
Nicholas Milton | 2 | Done | 27 |  | Target audience research | Must | half an hour | 0.5 | Added to powerpoint and prep for presentation | 0.5 | 0 | 89 | 178 | 178
Stephanie Reed | 2 | Done | 43 |  | Fix Github Conflict | Must | half an hour | 0.25 |  | 0.5 | -0.3 | 89 | 178 | 356
Sean Miyaoka | 2 | Done | 45 |  | Wireframe - User Registration Overlay | Must | half an hour | 0.5 |  | 0.5 | 0 | 89 | 178 | 178
Sean Miyaoka | 2 | Done | 46 |  | Wireframe - User Login Overlay | Must | half an hour | 1 | Changed from full page to Overlay | 0.5 | 0.5 | 89 | 178 | 89
Stephanie Reed | 2 | Done | 16 |  | Confirm when lab booking opens | Should | a few minutes | 0.1 | Thursday 8:30am | 0.2 | -0.1 | 20 | 100 | 200
Stephanie Reed | 2 | Done | 17 |  | Setup Brackets and temporary workspace | Should | a few minutes | 0.2 |  | 0.2 | 0 | 20 | 100 | 100
Stephanie Reed | 2 | Done | 21 |  | Clean up rotation script | Should | a few minutes | 0.2 |  | 0.2 | 0 | 20 | 100 | 100
Sean Miyaoka | 2 | Done | 4 |  | Wireframe - Start Screen | Must | an hour | 0.5 | Very simple start screen | 1 | -0.5 | 89 | 89 | 178
Sean Miyaoka | 2 | Done | 5 |  | Wireframe - Main Combat Screen | Must | an hour | 1.5 | UI setup should be discussed | 1 | 0.5 | 89 | 89 | 59.33
Sean Miyaoka | 2 | Done | 6 |  | Wireframe - Trivia Screen | Must | an hour | 1 | Looks acceptable | 1 | 0 | 89 | 89 | 89
Sean Miyaoka | 2 | Done | 7 |  | Wireframe - Home Screen | Must | an hour | 1 | Depending on implementation, should be discussed | 1 | 0 | 89 | 89 | 89
Whole Team | 2 | Done | 15 |  | Tuesday Lecture | Must | an hour | 1 |  | 1 | 0 | 89 | 89 | 89
Nicholas Milton | 2 | In Progress | 26 |  | Powerpoint presentation | Must | an hour | 1 | Loaded onto github docs | 1 | 0 | 89 | 89 | 89
Adam Hsu | 2 | Done | 31 |  | ArtWork(LOGO) | Must | an hour | 1 |  | 1 | 0 | 89 | 89 | 89
Sean Miyaoka | 2 | Done | 34 |  | Wireframe - Start Screen | Must | an hour | 1 | Changed to vertical | 1 | 0 | 89 | 89 | 89
Sean Miyaoka | 2 | Done | 35 |  | Wireframe - Main Combat Screen | Must | an hour | 1 | Changed to vertical and added final page | 1 | 0 | 89 | 89 | 89
Sean Miyaoka | 2 | Done | 36 |  | Wireframe - Trivia Screen | Must | an hour | 1 | Changed to vertical | 1 | 0 | 89 | 89 | 89
Sean Miyaoka | 2 | Done | 37 |  | Wireframe - Home Screen | Must | an hour | 1 | Changed to vertical | 1 | 0 | 89 | 89 | 89
Stephanie Reed | 2 | In Review | 39 |  | Make adjustments to the screen flow diagram | Must | an hour | 2.5 |  | 1 | 1.5 | 89 | 89 | 35.6
Sean Miyaoka | 2 | Done | 44 |  | Wireframe - Character Select | Must | an hour | 1 |  | 1 | 0 | 89 | 89 | 89
Stephanie Reed | 2 | In Review | 2 |  | Write up naming conventions | Must | a couple of hours | 2 | Let me know what you think. | 2 | 0 | 89 | 44.5 | 44.5
Whole Team | 2 | Done | 12 |  | Monday Lecture | Must | a couple of hours | 2 |  | 2 | 0 | 89 | 44.5 | 44.5
Whole Team | 2 | Done | 13 |  | Monday Lab | Must | a couple of hours | 2 |  | 2 | 0 | 89 | 44.5 | 44.5
Whole Team | 2 | Done | 14 |  | Tuesday Lab and Assignment | Must | a couple of hours | 3.5 |  | 2 | 1.5 | 89 | 44.5 | 25.43
Stephanie Reed | 2 | Done | 19 |  | Experiment with rotating the website | Must | a couple of hours | 2 |  | 2 | 0 | 89 | 44.5 | 44.5
Nicholas Milton | 2 | In Progress | 20 |  | Experiment with Firebase database | Must | a couple of hours | 2 | Reported to team and need help with javascript | 2 | 0 | 89 | 44.5 | 44.5
Stephanie Reed | 2 | Done | 25 |  | Screen Flow Diagram | Must | a couple of hours | 2.2 | Loaded onto github docs | 2 | 0.2 | 89 | 44.5 | 40.45
Whole Team | 2 | Done | 40 |  | Thursday Lab: UI/UX Presentation Meeting | Must | a couple of hours | 2 |  | 2 | 0 | 89 | 44.5 | 44.5
Simon Chen | 2 | Done | 41 |  | Research on javascripting sidescroling game image implementation | Must | a couple of hours | 2 | got character image to appear so far. | 2 | 0 | 89 | 44.5 | 44.5
Whole Team | 2 | Done | 42 |  | Thursday Lecture | Must | a couple of hours | 2 |  | 2 | 0 | 89 | 44.5 | 44.5
Nicholas Milton | 2 | Done | 30 |  | Display data from firebase research | Should | half an hour | 0.5 |  | 0.5 | 0 | 20 | 40 | 40
Stephanie Reed | 2 | In Progress | 47 |  | Excel Spreadsheet | Should | an hour |  |  | 1 | -1 | 20 | 20 | #DIV/0!
Adam Hsu | 2 | Done | 22 |  | ArtWork(First round Charactars) | Must | a few hours | 2 |  | 5.5 | -3.5 | 89 | 16.18 | 44.5
Adam Hsu | 2 | Done | 29 |  | ArtWork(First round monsters) | Must | a few hours | 2.5 |  | 5.5 | -3 | 89 | 16.18 | 35.6
Adam Hsu | 2 | Rejected | 32 |  | PPT UI | Must | a few hours | 2.5 |  | 5.5 | -3 | 89 | 16.18 | 35.6
Adam Hsu | 2 | In Progress | 33 |  | PPT UI | Must | a few hours | 1 | adjusting UI | 5.5 | -4.5 | 89 | 16.18 | 89
Stephanie Reed | 2 | Done | 23 |  | Mobile viewport research | Should | a couple of hours | 1 | No longer relevant | 2 | -1 | 20 | 10 | 20
Whole Team | 2 | Done | 24 |  | Wednesday Lab: UI/UX Meeting | Should | a couple of hours | 2 |  | 2 | 0 | 20 | 10 | 10
Sean Miyaoka | 2 | In Progress | 28 |  | Research potential food trivia questions | Should | a few hours | 2 | Still need a lot more questions | 5.5 | -3.5 | 20 | 3.64 | 10

## Calculations (DO NOT TOUCH)
FALSE | FALSE
FALSE | 0.2
FALSE | FALSE
FALSE | FALSE
FALSE | 0.15
FALSE | FALSE
FALSE | 0.5
FALSE | 0.2
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | 1
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | 2
FALSE | 2
FALSE | 3.5
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | 2
FALSE | FALSE
FALSE | 2
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | FALSE
FALSE | 2
FALSE | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE
0 | FALSE